### Project Plan
This section outlines the detailed plan for executing the data mining project, translating the business and data mining goals into a structured, time-bound, and resourced-based work breakdown. The plan is organized into four distinct phases that align with the CRISP-DM methodology.
#### 1.5.1. Executive Summary & High-Level Timeline
The primary goal is to deliver an automated topic-classification pipeline for judicial judgments using supervised Natural Language Processing (NLP). The solution must meet the defined success criteria, including achieving a target accuracy of ≥86%, reducing manual review time, and securing positive stakeholder feedback. The project is structured across four phases, with a focus on iterative development to manage key constraints such as data availability and computational resources.
Phase	Dates (2025)	Duration (Days)
1. Business & Data Understanding	11 Aug – 14 Aug	4
2. Data Preparation	15 Aug – 19 Aug	5
3. Modelling (with iterations)	20 Aug – 24 Aug	5
4. Evaluation & Deployment Plan	25 Aug – 29 Aug	5

#### 1.5.2. Phase-by-Phase Plan
##### Phase 1: Business & Data Understanding (11–14 Aug)
- Goal: To finalize project scope, confirm requirements with stakeholders, and secure initial data access.
- Tasks:
  - Day 1 (11 Aug): Project kickoff and stakeholder interviews to define topic categories, acceptable error rates, and key performance indicators (KPIs).
  - Day 2 (12 Aug): Document requirements and formalize acceptance criteria.
  - Day 3 (13 Aug): Identify data sources (e.g., court repositories) and request access to extract an initial data sample (≈ 10-50 judgments per category).
  - Day 4 (14 Aug): Conduct a quick quality assessment of the data sample (e.g., OCR quality, class imbalance) and finalize the data annotation plan.
- Resources: Project lead, data scientist, legal subject matter expert (SME), and a data engineer.
- Dependencies: Timely approval for data access is a critical path item. Delays here will directly impact subsequent phases.
##### Phase 2: Data Preparation (15–19 Aug)
- Goal: To create a clean, annotated, and version-controlled dataset ready for modeling.
- Tasks:
  - Day 5 (15 Aug): Set up the annotation tool (e.g., Label Studio) and train labelers on the established guidelines.
  - Day 6-7 (16-17 Aug): Annotate a small seed dataset (≈ 200-300 judgments) and perform an inter-rater reliability check to ensure consistency.
  - Day 8 (18 Aug): Perform preprocessing steps including OCR cleanup, normalization, and initial feature extraction (e.g., TF-IDF).
  - Day 9 (19 Aug): Create a stratified train, validation, and test split, and version the final dataset.
- Resources: Data engineer, 1-2 labelers, and a legal SME for quality assurance.
- Dependencies: This phase is entirely dependent on the successful completion of data extraction in Phase 1.
##### Phase 3: Modelling & Iterations (20–24 Aug)
- Goal: To develop and tune a robust classification model that meets the performance criteria. This phase is designed to be iterative.
- Tasks:
  - Day 10 (20 Aug): Establish a baseline model using a simple approach (e.g., TF-IDF with SVM or Logistic Regression) and evaluate its performance.
  - Day 11-12 (21-22 Aug): Develop and train an advanced model, such as a fine-tuned transformer (e.g., BERT), and perform hyperparameter tuning.
  - Day 13-14 (23-24 Aug): Conduct two planned iterations to refine the model. This includes addressing identified weaknesses (e.g., through data augmentation, class weighting) and selecting the final model.
- Resources: ML engineer, data scientist, and a GPU-enabled cloud environment (e.g., Google Colab).
- Dependencies: This phase relies on the availability of the prepared labeled dataset from Phase 2 and sufficient computational resources (GPU access) for advanced models. A fallback plan (using simpler models like SVM) will be used if GPU access is a limiting factor.
##### Phase 4: Evaluation, UAT & Deployment Plan (25–29 Aug)
- Goal: To finalize model performance, validate it with end-users, and create a clear plan for system deployment and integration.
- Tasks:
  - Day 15 (25 Aug): Final evaluation of the selected model against all technical KPIs (e.g., accuracy, runtime).
  - Day 16 (26 Aug): Conduct User Acceptance Testing (UAT) with legal SMEs to gather feedback on usability and trust, targeting ≥80% positive feedback.
  - Day 17-18 (27-28 Aug): Prepare deployment artifacts (e.g., serialized model, API specifications) and create a formal integration plan for connecting the model to existing legal databases.
  - Day 19 (29 Aug): Final project presentation to stakeholders and formal sign-off.
- Resources: ML engineer, DevOps/infra specialist, legal SME, and the project lead.
- Dependencies: This phase is contingent on the successful completion of the modeling phase and requires active participation from stakeholders for UAT and sign-off.
#### 1.5.3. Risk Analysis & Mitigation
Several risks have been identified, and a contingency strategy is in place to ensure the project stays on track.
- Data Access & Quality: The highest risk. A delay in securing data access or poor OCR quality could halt the project. The mitigation strategy is to request data samples immediately and work in parallel on public data to build a prototype.
- Compute Availability (GPU): A high risk for advanced models. The mitigation is to reserve cloud resources in advance and have a fallback to lighter models if needed.
- Expert Availability: The limited availability of legal SMEs is a medium risk. This will be managed by scheduling specific time blocks for them and using a targeted sampling approach for reviews instead of full-document checks.
- Contingency Strategy: A two-iteration buffer is built into the modeling phase. In case of significant delays or unmet targets, the project scope may be reduced (e.g., focusing on only the highest-priority topics) to ensure a successful outcome within the allotted timeline.